## Schedule
| 3rd Feb | 10th Feb | 17th Feb | 24th Feb | 2nd March | 9th March | 16th March | 23rd March | 30th March | 6th April | 13th April | 20th April | 27th April | 4th May | 11th May | 18th May | 25th May | 1st June | 8th June | 15th June | 22nd June | 29th June | 6th July | 13th July | 20th July | 27th July | 3rd August | 10th August | 17th August | 24th August | 31st August | 7th September | 14th September | Notes
Define the goals and contents of my project | [6 empty] | ON HOLIDAY
Research difference between Oracle and MySQL and make a decision between the two
Research SDLC choices and decide on one for the project.
Think about how the database will be structured
Look into Python modules which may be useful
Set up base Python project with GIT version control
Install database software
Investigate similar studies for ideas. Document key findings
Find the best source for the Premier League statistics required
Investigate ML predictive algorithms and decide on 4 possibilities
Reflect on progress to date, what went well/bad.
Write TMA01 |  |  |  |  | 2020-03-03
CF1 - Gather data required
CF1 - Cleanse data.
CF1 - Insert data into database
CF1 - Create a database reset script
Write LEPSI review
CF2 - Plan how algorithm will work
CF2 - Do some more research for this algorithm on top of what has been done in the initial algorithm research
Write TMA02 | [10 empty] | 2020-04-14
Reevaluate project given feedback from tutor for TMA, make sure still makes sense
CF2 - Code the algorithm
CF2 - Test the finding
CF2 - Evaluate the Algorithm
CF2 - Produce graphs and report to show successfulness of the algorithm
CF2 - Reflect on CF2
CF3 - Plan how algorithm will work
CF3 - Do some more research for this algorithm on top of what has been done in the initial algorithm research
CF3 - Code the algorithm
CF3 - Test the finding
CF3 - Evaluate the Algorithm
CF3 - Produce graphs and report to show successfulness of the algorithm
CF3 - Reflect on CF3
Write TMA03 | [22 empty] | 2020-07-07
CF4 - Plan how algorithm will work
CF4 - Do some more research for this algorithm on top of what has been done in the initial algorithm research
CF4 - Code the algorithm
CF4 - Test the finding
CF4 - Evaluate the Algorithm
CF4 - Produce graphs and report to show successfulness of the algorithm
CF4 - Reflect on CF4
CF5 - Plan how algorithm will work
CF5 - Do some more research for this algorithm on top of what has been done in the initial algorithm research
CF5 - Code the algorithm
CF5 - Test the finding
CF5 - Evaluate the Algorithm
CF5 - Produce graphs and report to show successfulness of the algorithm
CF5 - Reflect on CF5
CF6 - Develop a feed from a sports website to pull in the latest fixtures
CF7 – Develop a user interface
Write EMA | [32 empty] | 2020-09-14
Note on E13: Away from 28th Feb - 3rd March. Ensure TMA is completed before this time.