## Schedule
| 3rd Feb | 10th Feb | 17th Feb | 24th Feb | 2nd March | 9th March | 16th March | 23rd March | 30th March | 6th April | 13th April | 20th April | 27th April | 4th May | 11th May | 18th May | 25th May | 1st June | 8th June | 15th June | 22nd June | 29th June | 6th July | 13th July | 20th July | 27th July | 3rd August | 10th August | 17th August | 24th August | 31st August | 7th September | 14th September | Notes
TMA01 |  |  |  | Note | 2020-03-03 |  | On Holiday
Identify the goals and contents of my project
Identify differences between Oracle and MySql
Choose an appropriate lifecycle and describe why the choice was made.
Start to design the database for storage of the data.
Look into Python modules which I might need but don't have experience with.
Set up base Python project with GIT version control
Install database
Look into similar studies/projects to give ideas. Document findings
Research into where I can find past premier league results and stats.
Investigate machine learning algorithms, identify 2-3 I could use.
Reflect on progress to date, what went well/bad.
Write TMA01
TMA02 | [10 empty] | 2020-04-14
Gather and cleanse data required
Reevaluate project given feedback from tutor for TMA, make sure still makes sense
Insert data into database
Determine if there are any legal, social, ethical and professional concerns to be aware of
Write the Python to read data from the database
Think about how I will program the algorithm chosen
Begin writing the code for algorithm 1 in Python
Write TMA02
TMA03 | [22 empty] | 2020-07-07
Look ahead, see what is feasible. Check ahead to see if still all doable
Reevaluate whether the algorithm chosen is still the correct choice
Write the Python code for algorithm 1 - this will involve lots of iteration/tweaking
Write the Python code for algorithm 2 - this will involve lots of iteration/tweaking
Check algorithm results
Review project so far, identify problems experienced any major issues which are on the horizon
Identify if current algorithm chosen is appropriate
Create graphs to show the learning aspect of the algorithm
Display results from algorithm 1 and 2
Write TMA03
EMA | [32 empty] | 2020-09-14
Reevaluate algorithms coded already
Write code for algorithm 3
Write code for algorithm 4
Write EMA
Note on E2: Away 28th Feb to 1st March. Possibly away 2nd and 3rd March with work.