## Schedule
| 3rd Feb | 10th Feb | 17th Feb | 24th Feb | 2nd March | 9th March | 16th March | 23rd March | 30th March | 6th April | 13th April | 20th April | 27th April | 4th May | 11th May | 18th May | 25th May | 1st June | 8th June | 15th June | 22nd June | 29th June | 6th July | 13th July | 20th July | 27th July | 3rd August | 10th August | 17th August | 24th August | 31st August | 7th September | 14th September | Notes
TMA01 |  |  |  |  | 2020-03-03 |  | On Holiday
Identify the goals and contents of my project
Look into similar studies/project which may have been undertaken.
Research into where I can find past premier league results and stats.
Identify differences between Oracle and MySql because I have used Oracle a lot more than MySql.
Look into Python modules which I might need but don't have experience with.
Choose an appropriate lifecycle and describe why the choice was made.
Look into starting to design the database for storage of the data.
Set up Python project
Set up database installation
Reflect on progress to date
Write TMA01
TMA02 | [10 empty] | 2020-04-14
Document progress in analysing problem and developing solution using techincal concepts and principles
Identify key information sources that will inform the project in the next phase
Review progress against your original plan, especially any practical activity
Evaluate legal, social, ethical and professional considerations arising from project
Reflect on approach to project work, identify positives and negatives, what's productive and what's not
Refine goals and content of project in light of feedback from tutor, reading and experience
Identify additional resources or unanticapated skills/activities and revise plan
Write TMA02
TMA03 | [22 empty] | 2020-07-07
Refine goals and contents of project in light of progress, plan final phase of project
Gather, analyse and evaulate revelant info to complete project
Demonstrate comprehension of the key literature underpinning the project by relating to project
Demonstrate and apply systematic understandng of fundamental technical concept and principles
Demonstrate and apply understand of context in which technical knowledge can be applied
Analyse a practical problem and devise and implement a solution building on knowledge and skills.
Demonstrate ability to report clearly and critically on outcomes of your project work
Reviewing progress against your project plan, identify major risks to success in next phase
Document appreciable progress towards developing a workable solution to chose problem
Write TMA03
EMA | [32 empty] | 2020-09-14
To be confirmed, this will involve finishing off unfinished pieces
Write EMA

## Schedule (TMA specific tasks)
| 3rd Feb | 10th Feb | 17th Feb | 24th Feb | 2nd March | 9th March | 16th March | 23rd March | 30th March | 6th April | 13th April | 20th April | 27th April | 4th May | 11th May | 18th May | 25th May | 1st June | 8th June | 15th June | 22nd June | 29th June | 6th July | 13th July | 20th July | 27th July | 3rd August | 10th August | 17th August | 24th August | 31st August | 7th September | 14th September | Notes
TMA01 |  |  |  |  | 2020-03-03 |  | On Holiday
Identify the goals and contents of your project
Select and evaluate info sources that describe related work and point to methods used
Identify resources that are crucical for success and assure availability when needed
Identify own skills and knowledge that are crucial for success and develop lacking skills
Choose an appropriate lifecycle model and schedule work required
Undertake some exploratory work to begin the project.
Reflect on progress to date
Write TMA01
TMA02 | [10 empty] | 2020-04-14
Document progress in analysing problem and developing solution using techincal concepts and principles
Identify key information sources that will inform the project in the next phase
Review progress against your original plan, especially any practical activity
Evaluate legal, social, ethical and professional considerations arising from project
Reflect on approach to project work, identify positives and negatives, what's productive and what's not
Refine goals and content of project in light of feedback from tutor, reading and experience
Identify additional resources or unanticapated skills/activities and revise plan
Write TMA02
TMA03 | [22 empty] | 2020-07-07
Refine goals and contents of project in light of progress, plan final phase of project
Gather, analyse and evaulate revelant info to complete project
Demonstrate comprehension of the key literature underpinning the project by relating to project
Demonstrate and apply systematic understandng of fundamental technical concept and principles
Demonstrate and apply understand of context in which technical knowledge can be applied
Analyse a practical problem and devise and implement a solution building on knowledge and skills.
Demonstrate ability to report clearly and critically on outcomes of your project work
Reviewing progress against your project plan, identify major risks to success in next phase
Document appreciable progress towards developing a workable solution to chose problem
Write TMA03
EMA | [32 empty] | 2020-09-14
To be confirmed, this will involve finishing off unfinished pieces
As above
As above
As above
As above
As above
As above
As above
Write EMA